Santa Rosa Junior College

Administrative Services

Final Report 2002-2003

| Objective Reference | Accomplishments | Support / Evidence / Comments |  |  |
| --- | --- | --- | --- | --- |
| 1.0 Objective 1.1 (The Vice President, Administrative Services will coordinate a systematic component assessment of the self-study planning statements and the visiting team's formal evaluation. | SRJC Accreditation Self-Study Response Respond to the Accreditation Self-study planning recommendations pertaining to Administrative Services Institutional Goals: #3 Program Development & Delivery, #10 Institutional Effectiveness Administrative Services, largely through the efforts of its Office of Institutional Research, has identified all planning and evaluation statements that require action and follow-up. Facilities Operations, Institutional Research, Computing Services and Environmental Health and Safety have further identified planning issues that require further action. During 2003-2004, further, more detailed work on each of the identified planning issues will be addressed by each of the Administrative Services sub-components. | Institutional Research, working with the Institutional Research Advisory Committee has identified all Accreditation Self-Study Planning Statements and Evaluation Team items which require further work. |  |  |
| 2.0 Objective 2.1 (Complete design of new library and commence planning of projects identified as "secondary impacts.") | Develop a comprehensive plan for completion of the working drawing design phase of the new Learning Resource Center (Library) on the Santa Rosa Campus, and initial planning and design phases of building projects generated by the new Library. Institutional Goals: #1 Instructional Quality, #3 Program Development & Delivery, #10 Institutional Effectiveness. The working drawings have been completed and approved by the Division of State Architecture (DSA) and the project is awaiting final release of construction funds. Secondary impact project planning has been completed for the demolition of Kent Hall, relocation of the Analy Temps to the Analy Village Modulars and for the Analy Hall Remodel Project. Projects have been bid and work will be complete in Fall, 2003. | Working Drawings approved by DSA in April, 2003. Demolition of Kent Hall, construction of Analy Village and remodel of Analy Hall will commence in early Summer, 2003. |  |  |
| 3.0 Objective 3.1 (Develop and implement a Modernization and Utilization Plan for Analy Hall and Baker Hall.) | Develop a long-range Modernization and Utilization Plan for vacant educational spaces in Analy Hall and Baker Hall. Institutional Goals: #3 Program Development & Delivery, #4 Resource Development, #10 Instructional Effectiveness.. Analy Hall Jewelry Lab has been relocated to Santa Rosa High School. Analy Art Lab project awaiting funding. The Analy Hall Remodel Project connecting to the new Library will commence construction in June, 2003. Baker Hall renovation is under construction. | Analy Hall and Baker Hall Remodel drawings were completed, the Board approved the projects for bid and contracts have been awarded. |  |  |
| 4.0 Objective 4.1 (Provide a renewed educational facilities plan based on the completed Educational Master Plan and Student Services Plan and identified major Scheduled Maintenance needs.) | Administrative Services, in conjunction with other component areas and the Institutional Planning Council, will develop a refined Strategic Capital Projects Plan (including the Five-Year Capital Outlay Program) in response to the College's Integrated Master Plan. Institutional Goals: #1 Instructional Quality, #3 Program Development & Delivery, #4 Resource Development, #11 Fiscal Responsibility The master space planning consultant’s work is completed and has been presented, in summary form, to the Board of Trustees. The component administrators will review and discuss leading to a planning review by the Board Facilities Committee (BFC). The current Five Year Capital Outlay Program will reflect pre-Measure A planning. The 2004 submittal will reflect the results of the master planning process. |  | Administrative Services has completed the Strategic Capital Outlay Plan and will submit a 2003 Five-Year Plan submittal based upon it. |  |
| 5.0 Objective 5.1 (Collaborate with all segments of the institution to develop functional specifications that describe present and future Administrative Software needs) | Computing Services will develop a plan to address present and future needs of Administrative Software Systems at Santa Rosa Junior College. Institutional Goals: #1 Instructional Quality, #3 Program Development & Delivery, #10 Institutional Effectiveness A cross component “Administrative Software Task Force” has been formed and is meeting on a periodic basis to develop functional specifications for future Administrative Software needs. A document has been developed “Task Force and Assessment Teams” that describes an organizational structure and a process that will help Santa Rosa Junior College determine the future direction of its Administrative Software Systems |  | View the following web page for details of the “Administrative Software Task Force” team: http://www.santarosa.edu/ERP/ASTF-org-chart.pdf View the following web page for the details of the developed “Task Force and Assessment Teams” http://www.santarosa.edu/ERP/ERP-ASTF-ART-teams1.pdf |  |
| Objective 5.2 (In conjunction with the Foundation for California Community Colleges, develop and issue a RFP that defines our Administrative Software needs) | A draft “Request for Proposal” has been developed and is currently being reviewed by various members of the College Community. |  | To view a copy of the draft “Request for Proposal” go to the following link: http://www.santarosa.edu/ken/RFP-Drat-for-District-First-Review.doc |  |
| Objective 5.3 (Evaluate vendor responses to RFP and prepare plan for institutional review) | This is a work in progress and is projected to be completed in October of 2003. |  |  |  |
| 6.0 Objective 6.1 (Gain exposure and support for the "Strategic Master Plan for Technology) | Collaborate with all segments of the College to implement the recommendations presented in the "Strategic Master Plan for Technology." Institutional Goals: #1 Instructional Quality, #3 Program Development & Delivery, #10 Institutional Effectiveness The “Strategic Master Plan for Technology 2002 and Beyond” has been reviewed by Dr. Agrella and the Component Administrators. A copy of the master plan is available in the College Library and can be down loaded from Public Folders in Outlook. |  | To view a copy of the “Strategic Master Plan for Technology” go to Public Folders in Outlook and find “Committees” then ITG |  |
| Objective 6.2 (Identify projects in the "Strategic Master Plan for Technology" on Web and hardcopy) | The following list of projects have been extracted from the “Strategic Master Plan for Technology” as top priorities and if funding is available they will be completed over the next five years. Building to Building Connectivity & Infrastucture - Maggini Hall Network Replacement - Uninterruptable Power Supply - Wireless Systems - Upgrade Telephonic Systems - Integrated College Records Systems Preliminary Design - College Site Software Licenses - Instructional Computer Upgrades - Institutional & Instructional Technology Equipment Replacements |  | See list of Bond Projects 1st $60 Million Sale. |  |
| Objective 6.3 (On an annual basis review and revise the "Strategic Master Plan for Technology" with the Institutional Technology Group) | ITG (Institutional Technology Group) meets twice a month and is projecting completion of the revised “Strategic Master Plan for Technology” in October 2003. |  |  |  |
| Objective 6.4 (Identify Computing Service' impact on those projects in the "Strategic Master Plan for Technology" that received funding in 2002/2003. | Building-to-Building Connectivity has been improved by adding 22 high speed switches to various campus buildings and redundant network components have been added to the main Cisco 6513 backbone switch. Laptops have been purchased to allow Network Technicians to monitor and manage the network. Wiring in instructional labs, Shuhaw, Bussman, and Lark has been redone to bring them up to current standards. 50 desktop computers have been ordered and are being installed. These new computer systems will replace outdated technology. Several institutional servers have been replaced including: the main web server (Grimmy), the main DNS server, and the main monitoring server (Services). A new tape drive system to backup our mail servers has been acquired and implemented. A new server has been acquired to develop web based applications such as our new Community Education registration system. |  | See servers and switches in Bussman, Forsyth, Haehl, Bailey, Analy Temps, Staff Resources, Graphic Services, Call Center, Burbank, Doyle, EOPS, Shuhaw, Baker, Lark, Button, and Pedroncelli. |  |
| 7.0 Objective 7.1 (Identify and prioritize Institutional Research needs, in concert with the Institutional Planning Council (IPC), Institutional Research Advisory Group (IRAG) | Administrative Services and the Office of Institutional Research (OIR) will refine and implement a comprehensive research agenda for the college during 2002-2003. Institutional Goals: #2 Student Success, #4 Resource Development, #5 Student Retention and Persistence, #10 Institutional Effectiveness, #13 Institutional Advocacy The Institutional Advisory Group (IRAG) met monthly during the 2002-03 academic year with the primary function of prioritizing research requests and setting the research agenda. The Director of Institutional Research regularly provided updates at IPC meetings. |  | IPC minutes, IRAG agendas |  |
| Objective 7.2 (Assist and support Student Services in conducting mandated matriculation research) | The Office of Institutional Research continues to conduct mandated matriculation research. This year, the list included: implementing English placement and ESL placement without a writing sample; pilot testing the CTEP assessment for English Placement; EMC 270A prerequisite study; initial studies to renew approval for the Chemistry placement process. |  | Reports and various other documentation |  |
| Objective 7.3 (Improve research dissemination to better inform the campus community) | In Fall 2002, the Office of Institutional Research launched a website, which provides a wealth of links to data and information to support planning at SRJC. The website includes the full text of Fact Book 2001 and Fact Book 2002. In addition, “Weekly Facts” were e-mailed to campus staff during Winter 2003, and they will resume again in Fall 2003. Institutional Research also presented at the Fall 2002 and Spring 2003 PDA Days. |  | http://www.santarosa.edu/research; PowerPoint presentations and handouts from PDAs, e-mail text from “Weekly Facts” |  |
| 8.0 Objective 8.1 (EH&S will update existing conditions at the Petaluma Campus regarding hazardous materials labeling and storage) | EH&S will improve compliance with regulatory environmental safety and health mandates within the district. Institutional Goals: #10 Institutional Effectiveness - Chemical labels were replaced with newer, more informative ones in the Life Science (Biology) area. - A new 45-gallon flammable cabinet was purchased for the Art Department to store mineral spirits used in painting classes. - Six, new one-gallon containers used for mineral spirits storage were purchased, eliminating the need for the cumbersome two-and-one-half-gallon containers that had been used for years. - A new 30-gallon pesticide cabinet was purchased for safer storage of pesticides used by the grounds/maintenance department. - Various safety signs were posted in campus labs instructing staff and students in the safe handling and storage of hazardous materials. |  | District funds were identified and spent to update and upgrade various aspects of the labeling and storage of hazardous materials on the Petaluma campus. Compliance with existing federal, state and local rules and regulations have been enhanced |  |
| Objective 8.2 (EH&S will develop and implement a new lock-out/tag-out safety program. | Two sessions of a two-hour certified course of instruction on Lock-out/Tag-out were presented on March 6 to District employees who are exposed to electrical or mechanical hazards in the course of servicing and maintaining machines and equipment. |  | On March 15, 2003, 15 high-risk employees completed two-hour certified Lock-out/Tag-out training. |  |
| 9.0 Objective 9.1 EH&S will assist in the development and implementation of District emergency preparedness plans. | EH&S will provide programs to improve the general health, wellness and emergency preparedness of the District through on-going educational events. Institutional Goals: #10 Institutional Effectiveness EH&S administered multiple aspects of the District’s emergency preparedness program during 2002-03: - 17 employees were trained in fire extinguisher use. - 112 employees were Red Cross trained and certified in Adult CPR. - 82 employees were Red Cross trained and certified in First Aid and AED use. - 103 employees and 37 students were trained in hazardous materials handling. - Emergency preparedness information was posted on the new EH&S website. - An executive briefing and program overview was developed and presented to the President’s Staff on March 17, 2003. Following this, the briefing was presented to component administrators and their managers. - The District’s first emergency preparedness handbook was written, approved by component administrators, printed and distributed to key District areas and contacts. |  | The District’s readiness for a disaster was enhanced through education and training programs and published information. |  |
| Objective 9.2 (EH&S will organize and sponsor, utilizing the SHAPE Committee as a work resource, a Fall 2002 Health, Wellness & Emergency Preparedness Fair and Staff Barbecue). | In conjunction with the District’s Safety and Health Awareness Program for Employees (SHAPE) Committee, EH&S organized and conducted a multi-faceted health and wellness fair on September 13, 2002, including vendor information booths, exhibits, hands-on demonstrations, classroom workshops, raffle donations, and luncheon for employees. |  | 35 private companies and public agencies along with an estimated 300 employees and students participated in SRJC’s first “Work-on-Wellness” Fair. |  |